## Agile Backlog 1
Iteration 1 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 101. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority (light green)
| Iteration 1 |  |  |  | Feature Enhancement
101 | Initial project setup and environment configuration | 2 PD | Akhil |  | Employer Management Hub
102 | Define user stories and deciding product backlog and sprint backlog | 1 PD | Karishma |  | Student Portal
102 a (Development Features) | Developing Student Portal - Start up | 2 PD | Sravan |  | Industry Searching
| Employer Management Hub - Start up |  |  |  | Job Recommendations
| Industry Searching - Start up |  |  |  | Advanced Job Search
103 | Backend API development (user authentication) | 4 PD | Akhil |  | Student Tracking
104 | Create initial database schema | 3 PD | Akhil |  | Q&A Feature
Profile Verification & Review
Calendar - Scheduling Events
| … |  |  |  | Content Management
Iteration 2
201 a | Implement frontend UI components for user dashboard | 5 PD | Neha
201 b (Development Features) | Developing Student Portal - Complete | 3PD | Sravan
Employer Management Hub - Complete
Industry Searching - Complete
Q&A Feature - Complete
Content Management - Start up
Calendar - Scheduling Events
202 | Integrate external APIs (payment gateway) | 3 PD | Akhil
203 | Revise entities and classes based on UI/UX feedback | 4 PD | Akhil
204 | Develop transaction processing module (e.g., checkout) | 4 PD | Akhil
205 | Unit testing for payment gateway integration | 3 PD | Sravan
Iteration 3
301 | Conduct integration testing for backend and frontend | 6 PD | Sravan
302 | Final UI improvements of all application based on testing feedback | 5 PD | Neha
303 | Perform regression testing on the entire system | 5 PD | Sravan
304 | Conduct acceptance and usability testing | 4 PD | Sravan
305 | Deployment to production environment | 3 PD | Neha
306 (Development Features | Job Recommendations | 5PD | Sravan
Advanced Job Search
Content Management - Complete
Profile Verification & Review
Low Priority (pink)
111 | Develop help and training manuals | TBD | Karishma
112 | Implement user activity logging and analytics | TBD | Sravan
| Medium Priority (light blue) |  |  | Note: assigned medium and low tasks are prioritized but not yet assigned to iteration, nor estimated.
107 | Design the error handling mechanisms and logging | TBD | Akhil
108 | Research third-party integrations for reporting | TBD | Neha

## Iteration 1 Plan
Iteration Plan 1
Project | Career Path Finder
Team Names: | Akhil, Karishma, Neha, Sravan
Team Number: | Group 1
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
101 | Initial project setup and environment configuration | Akhil | Yes
102 | Define user stories and project backlog | Karishma | Yes
102 a (Development Features) | Developing Student Portal - Start up | Sravan | Yes
Employer Management Hub - Start up
Industry Searching - Start up
103 | Backend API development (user authentication) | Akhil | Yes
104 | Create initial database schema | Akhil | Yes
105 | Define and implement basic frontend UI components | Neha | Yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Software architecture: Web app with a React frontend and Node.js backend | Scalability and performance as user load increases | Akhil
Database: MySQL | Ensuring relational integrity with complex data models | Akhil
Hosting: AWS or Azure | Potential cost increases with scale | Akhil
3. Did your team visually track your progress by using tools such as Microsoft Project, SharePoint, Trello, etc.? Explain why you choose this tool.
Tracking Software Used | Why?
Trello | Trello was selected because it's an easy-to-use, visual tool for tracking tasks. It provides a clear view of progress through the use of cards and lists, helping the team stay aligned on tasks, priorities, and deadlines.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 1
Iteration 1: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception PD | Iteration #1 PD | Iteration #2 PD | Iteration #3 PD | Transition PD
|  | Due: | Due: | Due: | Due: | Due:
101 | Brainstorming & Planning | 0 | 2 | 0 | 0 | 0
102 | Research on Market & Business Models | 0 | 2 | 0 | 0 | 0
103 | Develop Use Cases (Basic interactions) | 0 | 2 | 0 | 0 | 0
104 | Develop Entity Relationship Diagram (ERD) | 0 | 2 | 0 | 0 | 0
105 | Create Class Diagram for Entities and Relations | 0 | 2 | 0 | 0 | 0
106 | Initial Database Design and Schema Creation | 0 | 2 | 0 | 0 | 0
107 | Design Wireframes for UI Screens | 0 | 3 | 0 | 0 | 0
108 | Develop Mockups for Core Screens | 0 | 3 | 0 | 0 | 0
102a | Features Development | 0 | 2 | 0 | 0 | 0
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 80 | 0 | 0 | 0
Total Project Hours |  | 80

## Agile Backlog 2
Iteration 2 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
101 | Develop Database Tables (implement schema) | 3 | Akhil
102 | Implement Entity Relationships in Code | 3 | Akhil
104 | Implement Core Business Logic & Validation | 3 | Karishma
Iteration 2
201 | Implement Database Tables (apply schema) | 3 | Akhil
202 | Implement Entity Relationships in Code | 3 | Karishma
203 | Implement Core Business Logic & Validation | 3 | Akhil
204 | Design and implement UI mockups | 2 | Neha
205 | Define and finalize Use Cases | 2 | Neha & Karishma
206 | Begin Integration Testing | 2 | Sravan
207 | Create user documentation and training materials | 1 | Neha
201 b (Development Features) | Developing Student Portal - Complete | 3 | Sravan
Employer Management Hub - Complete
Industry Searching - Complete
Q&A Feature - Complete
Content Management - Start up
Calendar - Scheduling Events
304 | Integrate external APIs | 2 | Sravan
Iteration 3
301 | Finalize UI Design Implementation | 3 PD | Neha
302 | Implement User Authentication & Authorization | 3 PD | Karishma
306 (Development Features | Job Recommendations | 5 PD | Sravan
| Advanced Job Search | 5 PD | Sravan
| Content Management - Complete | 5 PD | Sravan
| Profile Verification & Review | 5 PD | Sravan
303 | Complete Payment Gateway Integration | 4 PD | Akhil
304 | Implement Core Business Logic and Validation | 3 PD | Karishma
305 | Test and Implement API Integrations | 3 PD | Sravan
306 a | Complete Database Integration | 3 PD | Akhil
307 | Conduct System Integration Testing (end-to-end) | 3 PD | Sravan
308 | Create Final User Documentation and Training Materials | 2 PD | Neha
Medium Priority
401 | Perform Security Audit and Fix Vulnerabilities | TBD | Akhil
402 | Conduct User Acceptance Testing (UAT) | TBD | Neha
403 | Finalize Performance Optimization | TBD | Sravan
404 | Integrate Third-Party Analytics Tool | TBD | Karishma
Low Priority
501 | Update and Refactor Code for Future Enhancements | TBD | Akhil
502 | Implement Feature Flagging for New Features | TBD | Neha
503 | Add Social Media Login Options | TBD | Karishma
504 | Write Detailed Technical Documentation for Devs | TBD | Sravan

## Iteration 2 Plan
Iteration Plan 2
Project | Career Path Finder
Team Names: | Akhil, Karishma, Neha, Sravan
Team Number: | Group 1
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
101 | Develop Database Tables (implement schema) | Akhil | Yes
201 b (Development Features) | Developing Student Portal - Complete | Sravan | Yes
Employer Management Hub - Complete
Industry Searching - Complete
Q&A Feature - Complete
Content Management - Start up
Calendar - Scheduling Events
102 | Implement Entity Relationships in Code | Akhil | Yes
104 | Implement Core Business Logic & Validation | Karishma | Yes
201 | Implement Database Tables (apply schema) | Akhil | Yes
202 | Implement Entity Relationships in Code | Akhil | Yes
203 | Implement Core Business Logic & Validation | Karishma | Yes
204 | Design and implement UI mockups | Neha | Yes
205 | Define and finalize Use Cases | Karishma | Yes
206 | Begin Integration Testing | Sravan | Yes
207 | Create user documentation and training materials | Neha | Yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
1. Database Management System (MySQL) | Potential performance issues with high volume of users | Akhil
2. Frontend (HTML, CSS, JavaScript, React) | UI scalability and responsiveness across devices | Neha
3. Backend (Node.js with Express) | Ensuring efficient API design and security | Karishma
4. Cloud Hosting (AWS) | Service downtime, cost management | Sravan
5. Payment Gateway Integration (Stripe) | Handling edge cases like failed transactions or payment retries | Akhil
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
Trello | Yes, we are using Trello to track tasks and progress.
GitHub | Yes, GitHub is being used for version control, code collaboration, and managing branches.
Progress | All tasks from Iteration 1 were completed, and tasks planned for Iteration 2 are in progress.
Updates | No major timeline changes, but minor adjustments have been made due to dependencies between tasks.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 2
Iteration 2: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and tasks must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
101 | Develop Database Tables (implement schema) | 0 | 2 | 0 | 0 | 0
102 | Implement Entity Relationships in Code | 0 | 2 | 0 | 0 | 0
104 | Implement Core Business Logic & Validation | 0 | 2 | 0 | 0 | 0
201 | Implement Database Tables (apply schema) | 0 | 0 | 2 | 0 | 0
202 | Implement Entity Relationships in Code | 0 | 0 | 2 | 0 | 0
203 | Implement Core Business Logic & Validation | 0 | 0 | 2 | 0 | 0
204 | Design and implement UI mockups | 0 | 0 | 3 | 0 | 0
205 | Define and finalize Use Cases | 0 | 0 | 2 | 0 | 0
206 | Begin Integration Testing | 0 | 0 | 2 | 0 | 0
207 | Create user documentation and training materials | 0 | 0 | 2 | 0 | 0
201b | Developing Features | 0 | 2 | 1 | 0 | 0
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 32 | 64 | 0 | 0
Total Project Hours |  | 96

## Agile Backlog 3
Iteration 3 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
All the tasks from iteration1 have been completed and nothing to be carried forward to this section
Iteration 2
All the tasks from iteration2 have been completed and nothing to be carried forward to this section
Iteration 3
301 | Finalize UI Design Implementation | 3 PD | Neha
302 | Implement User Authentication & Authorization | 3 PD | Karishma
306 a(Development Features | Job Recommendations | 5 PD | Sravan
| Advanced Job Search | 5 PD | Sravan
| Content Management - Complete | 5 PD | Sravan
| Profile Verification & Review | 5 PD | Sravan
303 | Complete Payment Gateway Integration | 4 PD | Akhil
304 | Implement Core Business Logic and Validation | 3 PD | Karishma
305 | Test and Implement API Integrations | 3 PD | Sravan
306 | Complete Database Integration | 3 PD | Akhil
307 | Conduct System Integration Testing (end-to-end) | 3 PD | Sravan
308 | Create Final User Documentation and Training Materials | 2 PD | Neha
| Medium Priority |  |  | Note: The tasks from medium and low priority are part of iteration 3 and have been assigned timelines, too, as this is the final sprint of the project.
401 | Perform User Acceptance Testing (UAT) | 3 PD | Neha
402 | Final Security Review and Fix Vulnerabilities | 2 PD | Akhil
403 | Final Performance Optimizations | 2 PD | Sravan
404 | Final Deployment (Deploy to Production Server) | 3 PD | Akhil
405 | Refactor Code and Cleanup for Final Delivery | 2 PD | Neha
Low Priority
501 | Finalize Project Documentation and API Architecture | 2 PD | Karishma
502 | Review and Close Project Management Tasks (e.g., final reports, project evaluation) | 1 PD | All

## Iteration 3 Plan
Iteration Plan 3
Project
Team Names:
Team Number:
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
301 | Finalize UI Design Implementation | Neha | Yes
302 | Implement User Authentication & Authorization | Karishma | Yes
306 a (Development Features | Job Recommendations | Sravan | Yes
| Advanced Job Search | Sravan | Yes
| Content Management - Complete | Sravan | Yes
| Profile Verification & Review | Sravan | Yes
303 | Complete Payment Gateway Integration | Akhil | Yes
304 | Implement Core Business Logic and Validation | Karishma | Yes
305 | Test and Implement API Integrations | Sravan | Yes
306 | Complete Database Integration | Akhil | Yes
307 | Conduct System Integration Testing (end-to-end) | Sravan | Yes
308 | Create Final User Documentation and Training Materials | Neha | Yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
- Frontend: ReactJS / Angular / HTML/CSS | - Cross-browser compatibility issues | Akhil
- Backend: Node.js / Express / Spring Boot | - Server load handling under stress | Karishma
- Database: MySQL / PostgreSQL / MongoDB | - Data migration and syncing challenges | Sravan
- Payment Gateway: Stripe / PayPal | - Integration with third-party services | Akhil
- Authentication: OAuth / JWT / Firebase Auth | - Security concerns regarding data breaches | Karishma
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
Trello | Yes, the team is still using Trello to track tasks and progress. The timeline remains on track, with major tasks in Iteration 3 expected to be completed by the end of this sprint. However, due to some adjustments to API testing, there may be a slight delay of 1-2 days in the final integration testing phase.
GitHub / GitLab | Yes, GitHub is used for version control and code collaboration.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 3
Iteration 3: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
301 | Finalize UI Design Implementation | 0 | 0 | 0 | 3 | 0
302 | Implement User Authentication & Authorization | 0 | 0 | 0 | 3 | 0
303 | Complete Payment Gateway Integration | 0 | 0 | 0 | 4 | 0
304 | Implement Core Business Logic and Validation | 0 | 0 | 0 | 3 | 0
305 | Test and Implement API Integrations | 0 | 0 | 0 | 3 | 0
306 | Complete Database Integration | 0 | 0 | 0 | 3 | 0
307 | Conduct System Integration Testing (end-to-end) | 0 | 0 | 0 | 3 | 0
308 | Create Final User Documentation and Training Materials | 0 | 0 | 0 | 2 | 0
401 | Perform User Acceptance Testing (UAT) | 0 | 0 | 0 | 3 | 0
402 | Final Security Review and Fix Vulnerabilities | 0 | 0 | 0 | 2 | 0
403 | Final Performance Optimizations | 0 | 0 | 0 | 2 | 0
404 | Final Deployment (Deploy to Production Server) | 0 | 0 | 0 | 3 | 0
405 | Refactor Code and Cleanup for Final Delivery | 0 | 0 | 0 | 2 | 0
501 | Finalize Project Documentation and API Architecture | 0 | 0 | 0 | 2 | 0
502 | Review and Close Project Management Tasks | 0 | 0 | 0 | 1.5 | 0
306 a | Full-Feature Developed | 0 | 0 | 0 | 10 | 0
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 0 | 0 | 198 | 0
Total Project Hours |  | 198